## Slide 1: Fondation Tanger Al Madina Statement of Work
IBM Corporate Services Corps – Morocco
May 24, 2013

## Slide 2: Our approach & deliverables
Conduct kick off meetings
Identify existing documentation/resources
Finalize scope / approach / deliverables
Identify and contact data sources
Activities
Deliverables
Time
Conduct 1-on-1 FTAM director interviews
Collect data from stakeholders (email survey)
Capture / categorize findings
Develop business design framework
Initiate project
Gather & synthesize data
Identify business design options
Develop implementation plan
FTAM Strategic Plan: Statement of Work
May 21 – June 13
Develop business design options incl. organizational identity and governance, mission, goals and success metrics
Build operational options including portfolio of offerings, resources, partnerships and communications
Develop implementation plan of the selected design option & review findings and recommendations with FTAM
Revised SOW / project approach
Synthesis of our understanding of current challenges & issues and operational model
SWOT analysis
2-3 business design options for next 1-3 years with associated benefits & risks
Strategic recommendations for short-term sustainability and long-term growth
Communication package
Implementation plan
2 days (complete)
1-2 weeks
1 week
1 week
1
2
3
4

## Slide 3: Timing & milestones
1. Initiate project
  Conduct kick off meetings
  Identify existing documentation/resources
  Finalize scope / approach / deliverables
  Identify and contact data sources
2. Gather data & synthesize
Conduct 1-on-1 FTAM director interviews
Conduct 1-on-1 other stakeholder interviews
Capture / categorize findings (SWOT)
Develop strategic plan framework
3. Identify business design options
Develop business design options incl. organizational identity and governance, mission , goals and success metrics
Build operational options including portfolio of offerings , resources, partnerships and communications
4. Develop implementation plan
Develop implementation plan of the selected option & review findings and recommendations with FTAM
Activities
By week ending
May 24
May 31
June 13
June 7
Joint kick off
Workshop & decision on option to develop
Final presentation
Checkpoint meeting